## VOLUNTEER preferences
EU security DevSecOps Reference Design initiative
Volunteer preferences form
Full name | [9 empty] | Organisation | [9 empty] | Email | [9 empty] | Primary role(s)
Short CV (focus mainly on the DevSecOps related experience/knowledge)
Please select the preferred roles you would like to play, specifying it for each section/part of the EU public DevSecOps Reference Design document.
(*) Mark with a "1" the cells that correspond to the roles that you would like to play
Introduction |  |  | Assumptions&Principles |  |  | DevSecOps Concepts |  |  | Phase 1 - PLAN |  |  | Phase 2 - DEVELOP |  |  | Phase 3 - BUILD |  |  | Phase 4 - TEST |  |  | Phase 5 - RELEASE |  |  | Phase 6 - DELIVER |  |  | Phase 7 - DEPLOY |  |  | Phase 8 - OPERATE |  |  | Phase 9 - MONITOR |  |  | Phase 10 - FEEDBACK |  |  | Conclusion |  | APPENDIXES
editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | contributor | reviewer | editor | reviewer | editor | reviewer
Different roles with different levels of participation:
Section editors: ~20-40 hours total of estimated effort
• Report to the “document co-editors”
• Manage and coordinate the work of the “contributors”
• Ensure that the section's content is of as high-quality as possible, delivered in a timely manner, and in compliance with the guide/manual provided by the document editors
Contributors: ~8-16 hours total of estimated effort (per section they contribute to, in case they contribute to more than one)
• Provide their contributions as per the guide/manual for “contributors” in a timely manner
Reviewers: ~4-8 hours total of estimated effort
• Review the document and/or the sections assigned to them and provide the feedback as instructed
Work plan: |  |  |  | start Mar'23 - end Oct'23
see "work-plan" sheet for details.

## work-plan
DevSecOps Reference Design v1.0 preparation work-plan
|  |  |  | February |  |  |  |  | March |  |  |  | April |  |  |  | May |  |  |  | June |  |  |  |  | July |  |  |  | August |  |  |  |  | September |  |  |  | October |  |  |  | November …
|  |  |  | w1 | w2 | w3 | w4 | w5 | w6 | w7 | w8 | w9 | w10 | w11 | w12 | w13 | w14 | w15 | w16 | w17 | w18 | w19 | w20 | w21 | w22 | w23 | w24 | w25 | w26 | w27 | w28 | w29 | w30 | w31 | w32 | w33 | w34 | w35 | w36 | w37 | w38 | w39 | w40 | w41 | w42
ID | Task / Activity / Milestone | Owner | Participant(s) | time axis 2023-01-30 to 2023-11-13
0 | Build minim. Consensus and the doc “co-editors” group | Juan A. | bar: 2023-01-30
0.1 | Discuss & agree the Table of Contents (ToC) of the doc | Doc-editors | bar: 2023-02-06
0.2 | Public call for contributors | Doc-editors | bar: 2023-02-06 to 2023-02-27
0.3 | Create how-to guides for section-editors, contributors, and reviewers | Doc-editors | bar: 2023-02-06 to 2023-02-20
0.4 | Decide about "section-editors" and contributors to sections | Doc-editors | bar: 2023-02-27
0.5 | Kick-off with "section-editors" | Doc-editors | Section-editors | bar: 2023-02-27
1 | "Section-editors" to launch their teams | Section-editors | Contributors | bar: 2023-03-06
1.1 | "Contributors" to submit their parts | Contributors | Section-editors | bar: 2023-03-06 to 2023-03-20
1.2 | "Section-editors" to consolidate the first version of their sections | Section-editors | bar: 2023-03-27
1.3 | "Document editors" to review and request changes/improvements | Doc-editors | bar: 2023-04-03 to 2023-04-10
1.4 | "Section-editors" to make changes/improvements as requested | Section-editors | Contributors | bar: 2023-04-17 to 2023-04-24
1.5 | "Document editors" to prepare the "pre-final" version of the doc | Doc-editors | bar: 2023-05-01 to 2023-05-08
1.6 | "Reviewers" to review and provide their feedback | Reviewers | bar: 2023-05-15 to 2023-05-22
1.7 | "Section-editors" to make changes/improvements as needed | Section-editors | bar: 2023-05-29 to 2023-06-05
1.8 | "Document editors" final check and changes (if/as needed) | Doc-editors | bar: 2023-06-12 to 2023-06-19
2 | Publish the "Preprint" version > publicky - asking for feedback | Doc-editors | bar: 2023-06-26
2.1 | Receive feedback from the community | Doc-editors | Section-editors | bar: 2023-06-26 to 2023-09-04
2.2 | "Section-editors" to make changes/improvements as needed | Section-editors | Contributors | bar: 2023-09-04 to 2023-09-11
2.3 | "Document editors" final check and changes (if/as needed) | Doc-editors | bar: 2023-09-18 to 2023-09-25
2.4 | Publish the FINAL v1.0 version of the document | Doc-editors | bar: 2023-09-25
3 | Public call for volunteers to create v2.0 (to be published 1 year later) | Doc-editors | Section-editors | bar: 2023-10-02 to 2023-10-23
3.1 | Decide about "Document editors" for v2.0 | Doc-editors | bar: 2023-10-30
3.2 | Decide about "section-editors" and contributors to sections for v2.0 | Doc-editors | bar: 2023-11-06
3.3 | Kick-off with "section-editors" | Doc-editors | Section-editors | bar: 2023-11-13
3.4 | …. (TBC by the "new" v2.0 team) | … | …